## Trang tính1
No. | Entity name |  | Coding-Status | Coding Plan Timeline | In-charge full name | No. | Function name | Feature | SRS
1 | Product | Entity | 100% | 24/6~26/6 | Nguyễn Tấn Dũng | 1 | Login | Admin | Done
|  | Repository | 100% | 24/6~26/6 | Nguyễn Tấn Dũng | 2 | Logout | Admin | Done
|  | Service | 100% | 27/6~28/6 | Nguyễn Tấn Dũng | 3 | view product | Admin, Customer | Done
|  | API | 60% | 1/7~4/7 | Nguyễn Tấn Dũng | 4 | add product to cart | Customer | Done
|  | Validation | 0% | 6/7~10/7 |  | 5 | view cart | Customer | Done
2 | Category | Entity | 100% | 24/6~26/6 | Đoàn Trọng Khôi | 6 | update product in cart | Customer | Done
|  | Repository | 100% | 24/6~26/6 | Đoàn Trọng Khôi | 7 | delete product from cart | Customer | Done
|  | Service | 100% | 27/6~28/6 | Đoàn Trọng Khôi | 8 | view category | Admin, Customer | Done
|  | API | 0% | 1/7~4/7 | Đoàn Trọng Khôi | 9 | checkout | Customer | Done
|  | Validation | 0% | 6/7~10/7 |  | 10 | view product detail | Admin, Customer | Done
3 | Order | Entity | 100% | 24/6~26/6 | Đinh Bá Tuấn Ngọc | 11 | search | Admin, Customer | Done
|  | Repository | 100% | 24/6~26/6 | Đinh Bá Tuấn Ngọc | 12 | view shopping history | Customer | Done
|  | Service | 100% | 27/6~28/6 | Đặng Đức Toàn | 13 | create product | Admin | Done
|  | API | 0% | 1/7~4/7 | Đặng Đức Toàn | 14 | update product | Admin | Done
|  | Validation | 0% | 6/7~10/7 |  | 15 | delete product | Admin | Done
4 | Manufacturer | Entity | 100% | 24/6~26/6 | Trần Thị Dịu Hương | 16 | create category | Admin | Done
|  | Repository | 100% | 24/6~26/6 | Trần Thị Dịu Hương | 17 | update category | Admin | Done
|  | Service | 100% | 27/6~28/6 | Nguyễn Hải Quang | 18 | delete category | Admin | Done
|  | API | 0% | 1/7~4/7 | Nguyễn Hải Quang, Nguyễn Lê Anh | 19 | view order | Admin | Done
|  | Validation | 0% | 6/7~10/7 |  | 20 | update order | Admin | Done
5 | Location | Entity | 100% | 24/6~26/6 | Nguyễn Lê Anh | 21 | delete order | Admin | Done
|  | Repository | 100% | 24/6~26/6 | Nguyễn Lê Anh
|  | Service | 100% | 27/6~28/6 | Trần Thị Dịu Hương
|  | API | 0% | 1/7~4/7 | Trần Thị Dịu Hương
|  | Validation | 0% | 6/7~10/7
6 | Store | Entity | 100% | 24/6~26/6 | Nguyễn Hải Quang
|  | Repository | 100% | 24/6~26/6 | Nguyễn Hải Quang
|  | Service | 100% | 27/6~28/6 | Đinh Bá Tuấn Ngọc
|  | API | 0% | 1/7~4/7 | Đinh Bá Tuấn Ngọc
|  | Validation | 0% | 6/7~10/7
finish task ontime
FE | 0/7 |  | 0% |  | cant finish task
BD | Done |  | 100% |  | finish task but overtime
on progress
future