## MANAGE ENTITY
No. | Entity name |  | Coding-Status | Test-Status | Coding Plan Timeline | In-charge full name | No. | Function name | Feature | SRS | API For Function
1 | Product | Entity | 100% |  | 24/6~26/6 | Nguyễn Tấn Dũng | 1 | Login | Admin | Done
|  | Repository | 100% |  | 24/6~26/6 | Nguyễn Tấn Dũng | 2 | Logout | Admin | Done
|  | Service | 100% |  | 27/6~28/6 | Nguyễn Tấn Dũng | 3 | view product | Admin, Customer | Done | /api/product, /api/productForCus
|  | API | 80% | 80% | 1/7~10/7 | Nguyễn Tấn Dũng | 4 | add product to cart | Customer | Done
|  | Validation | 0% |  | 15/7~20/7 |  | 5 | view cart | Customer | Done
2 | Category | Entity | 100% |  | 24/6~26/6 | Đoàn Trọng Khôi | 6 | update product in cart | Customer | Done
|  | Repository | 100% |  | 24/6~26/6 | Đoàn Trọng Khôi | 7 | delete product from cart | Customer | Done
|  | Service | 100% |  | 27/6~28/6 | Đoàn Trọng Khôi | 8 | find product by category | Customer | Done | /api/productByCategory/{id}
|  | API | 100% | 80% | 1/7~10/7 | Đoàn Trọng Khôi | 9 | checkout | Customer | Done
|  | Validation | 0% |  | 15/7~20/7 |  | 10 | view product detail | Admin, Customer | Done | /api/product/{id}
3 | Order | Entity | 100% |  | 24/6~26/6 | Đinh Bá Tuấn Ngọc | 11 | search | Admin, Customer | Done | /search/{id}
|  | Repository | 100% |  | 24/6~26/6 | Đinh Bá Tuấn Ngọc | 12 | view shopping history | Customer | Done | /api/listOrderBySpecificPhone/{query}
|  | Service | 100% |  | 27/6~28/6 | Đặng Đức Toàn | 13 | create product | Admin | Done | /api/product
|  | API | 80% | 80% | 1/7~10/7 | Đặng Đức Toàn | 14 | update product | Admin | Done | /api/product/{id}
|  | Validation | 0% |  | 15/7~20/7 |  | 15 | delete product | Admin | Done | /api/product/{id}
4 | Manufacturer | Entity | 100% |  | 24/6~26/6 | Trần Thị Dịu Hương | 16 | view category | Admin, Customer | Done | /api/category, /api/categoryForcus
|  | Repository | 100% |  | 24/6~26/6 | Trần Thị Dịu Hương | 17 | create category | Admin | Done | /api/category
|  | Service | 100% |  | 27/6~28/6 | Nguyễn Hải Quang | 18 | update category | Admin | Done | /api/category/{id}
|  | API | 80% | 80% | 1/7~10/7 | Nguyễn Hải Quang, Nguyễn Lê Anh | 19 | delete category | Admin | Done | /api/deleteCategory/{id}
|  | Validation | 0% |  | 15/7~20/7 |  | 20 | view order | Admin | Done | /api/order
5 | Location | Entity | 100% |  | 24/6~26/6 | Nguyễn Lê Anh | 21 | update order | Admin | Done | /api/updateShippingStatus/{id}
|  | Repository | 100% |  | 24/6~26/6 | Nguyễn Lê Anh | 22 | create order | Admin | Done | /api/createOrder
|  | Service | 100% |  | 27/6~28/6 | Trần Thị Dịu Hương | 23 | find product by location | Customer | Done | /api/productByLocation/{id}
|  | API | 0% |  | 1/7~10/7 | Trần Thị Dịu Hương | 24 | View Manufacturer | Admin, Customer | Done | /api/manufacturer, /api/manufacturerForCus
|  | Validation | 0% |  | 15/7~20/7 |  | 25 | Create Manufacturer | Admin | Done | /api/manufacturer
6 | Store | Entity | 100% |  | 24/6~26/6 | Nguyễn Hải Quang | 26 | Update Manufacturer | Admin | Done | /api/updatemanufacturer/{id}
|  | Repository | 100% |  | 24/6~26/6 | Nguyễn Hải Quang | 27 | delete Manufacturer | Admin | Done | /api/updateStatusManufacturer/{id}
|  | Service | 100% |  | 27/6~28/6 | Đinh Bá Tuấn Ngọc | 28 | find product by manufacturer | Customer | Done | /api/productByManufacturer/{id}
|  | API | 40 |  | 1/7~10/7 | Đinh Bá Tuấn Ngọc
|  | Validation | 0% |  | 15/7~20/7
finish task ontime
FE | 2022-07-04 |  | 57% |  |  | cant finish task
BD | Done |  | 100% |  |  | finish task but overtime
on progress
future